**Sprint Planning Document – Phase 1, Sprint 1**

**🌍 Project:** Global Job & Relocation Platform **📅 Sprint Duration:** 2 Weeks (April 15 – April 29) **⏳ Sprint Goal:** Implement the foundation for user onboarding and job exploration

**🚀 Sprint Goal**

Build and test the core user onboarding, authentication, and basic job exploration pages, so early testers can start signing up and viewing jobs.

**🏋️ Team Members**

* Product Owner: [You]
* Scrum Master: [Name]
* Frontend Dev(s): [Names]
* Backend Dev(s): [Names]
* UI/UX Designer: [Name]
* QA: [Name]

**👥 Sprint Backlog (User Stories Selected from Product Backlog)**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Story ID** | **User Story** | **Story Points** | **Assignee** | **Status** |
| US-101 | As a user, I want to sign up using email, Google, or LinkedIn | 5 | Frontend Dev | To Do |
| US-102 | As a user, I want to be able to choose my user type | 3 | Frontend Dev | To Do |
| US-103 | As a user, I want to create a basic profile with resume upload | 5 | Backend Dev | To Do |
| US-104 | As a user, I want to log in securely and get redirected to the feed | 3 | Backend Dev | To Do |
| US-105 | As a user, I want to see a basic job listing with minimal UI | 3 | Frontend Dev | To Do |
| US-106 | As a user, I want to search and filter jobs | 5 | Frontend + Backend | To Do |

**Total Story Points Committed:** 24 (team capacity: 25 points)

**🔢 Sprint Planning Notes**

* Priority was given to user entry points and basic job visibility.
* Search experience and job UI are MVP-level (no metrics yet).
* Login flow uses Google/LinkedIn mock tokens for now.
* Resume uploads will be tested with dummy files.

**🔄 Dependencies**

* Finalized design specs for auth, profile, and job listing pages.
* Backend auth API must be live before end of Week 1.

**💡 Definition of Done (DoD)**

* Code committed to Git repo
* Unit tested (min 80% coverage)
* Feature demoed to PO
* Meets all acceptance criteria
* Passes QA review

**📈 Sprint Review Plan**

* Demo user sign up > profile > see jobs flow
* Share progress with early access stakeholders

**🤝 Sprint Retrospective Topics (To be filled at end of sprint)**

* What went well?
* What didn’t go as planned?
* What should we improve?